Northwest Tribal Epidemiology Center

(The EpiCenter)

January-March 2015 Quarterly Report

Northwest Tribal Epidemiology Center Projects’ Reports Include:

- Adolescent Health

- CDC Assignee

- Epicenter Biostatistician

- Injury Prevention Program (IPP)

- Maternal Child Health Projects

- Medical Epidemiologist

- Northwest Native American Research Center for Health (NARCH)

- Northwest Tribal Cancer Control Project

- Northwest Tribal Dental Support Center

- Northwest Tribal Registry Project-Improving Data and Enhancing Access (IDEA-NW)

- Wellness for Every American Indian to View and Achieve Health Equity (WEAVE)

- Western Tribal Diabetes Project

Adolescent Health

- Stephanie Craig Rushing, Project Director

- Colbie Caughlan, THRIVE Project Manager

- Jessica Leston, Project Manager

- Amanda Gaston, IYG Project Manager

- David Stephens, Multimedia Project Specialist

- Mattie Tomeo-Palmanteer, VOICES Coordinator

- Tommy Ghost Dog, Project Red Talon Assistant

- Celena McCray, THRIVE Project Assistant

- Students: Jenna Charlie, VOICES Data Entry Temp; Lauren Adrian, VOICES MPH Intern;

- Steven Hafner, Harvard PhD Student Intern; Patty Yao, OHSU PhD Student Intern

Quarterly Report: January – March 2015

Technical Assistance and Training

Tribal Site Visits

- NPAIHB QBM, Chehalis, WA, January 20-21, 2015.

- Heritage University & GLS Partnership, Toppenish, WA, February 12, 2015.

- We R Native. Northwest Indian Youth Conference, Ft Hall, ID, March 23-26, 2015.

- We R Native. BADD Tournament, Pendleton, OR, March 26, 2015.

Out of Area Tribal Site Visits

- Chicago Urban Clinic – January 9

- Montana Area Office, Tribal Epidemiology Center and Crow Agency – January 12-16.

- Arizona: PIMC, Pascua Yaki, Fort Yuma, Gila River – February

- Crow Improvement Intensive – March 2-6

Project Red Talon / We R Native

During the quarter, Project Red Talon staff participated in twenty-six planning calls, nine partner meetings, two youth outreach events, and presented at five conferences/webinars:

- Booth: We R Native. GONA, Portland, OR, March 23-24, 2015.

- Meeting: Adolescent Health Alliance Meeting, NPAIHB, March 19, 2015.

- Meeting: Dayna of AETC, February 9, 2015.

- Meeting: EpiCenter w/ Video Game Developer – Jack Snowden, February 11, 2015.

- Meeting: NPAIHB QBM, Chehalis, WA, January 20-21, 2015.

- Presentation and Booth: We R Native and Social Media. Northwest Indian Youth Conference, Ft Hall, ID, March 23-26, 2015.

- Presentation: We R Native and Social Media. AI/AN Men’s and Women’s Conference, San Diego, CA, March 23-26, 2015.

- Presentation: We R Native. BADD Tournament, Pendleton, OR, March 26, 2015.

- Training: HIV/STI/HCV Clinical Update PLUS Training, NPAIHB, March 18-19, 2015.

- Webinar: Native STAND Site Recruitment Q&A. February 4, 2015.

Native It’s Your Game

During the quarter, Native It’s Your Game staff participated in one face-to-face planning team meeting, twelve planning calls with study partners, and supported the following kick-off trainings and events:

- Kick-off Event: Nimiipuu Health Center, Lapwai, ID, January 30, 2015.

- NIYG 2nd Kick-off Event: Nimiipuu Health Center, February 6, 2015

- NIYG 2nd Kick-off Event: Shoshone-Bannock Counseling & Family Center, February 23, 2015

- NIYG Kick-off Event: Shoshone-Bannock Counseling & Family Center, February 9, 2015

- Training: ACF Sites (Pendleton and Shoshone-Bannock), January 27, 2015.

- Webinar: Native IYG program implementation; Shoshone-Bannock & Sunridge Middle School, February 11, 2015

- Meeting: NIYG National Planning Team Face-to-Face, Seattle, WA, March 17-18, 2015.

Native VOICES

During the quarter, Native VOICES staff participated in six planning meetings, launched the Native VOICES mini-series, and gave three regional/national presentations on the intervention:

- Launch: Native VOICES mini-series on FB, February 13, 2015.

- Presentation: Native VOICES Promotion for WTDB, March 03, 2015

- Presentation: Native VOICES Intervention, AI/AN Men’s & Women’s Wellness Conference, March 22, 2015

- Presentation: Native VOICES, QBM, Chehalis, WA, January 20, 2015.

Quality Improvement

During the quarter, STD/HIV QI staff participated in twenty-five planning calls, eighteen Adobe meetings, and hosted one regional training, including:

- Adobe: HIV prenatal panel fix – March 9

- Presentation: Chicago Urban Clinic Improvement Measures – January 9

- Training: NW AETC – March 18 and 19

- Webinar: ECHO – January 7, February 4, March 4

- Webinar: Great Plains ID Call – February 5

- Webinar: HCV Reminder with Great Plains Area – February 26

- Webinar: Hepatitis C National Presentation – January 8

- Webinar: Hepatitis C Panel review Jasmine and David – February 25

- Webinar: Holding the Gains IHI – January 7

- Webinar: I WANT THE KIT: Increasing access to STD Testing – February 4

- Webinar: IST Call – January 29, February 26, March 9

- Webinar: Monthly ID Planning Call with Great Plains – January 28, 2015

- Webinar: National Native HIV/AIDS Awareness Day – March 20

- Webinar: Obtaining the Latest Hepatitis C Medications using Patient Assistance Programs – January 22

- Webinar: Presentation STD/HIV/HCV to TEC Directors – January 15

- Webinar: Regional Infectious Disease Update GP/BEM/BIL – March 5

- Webinar: Review of Hepatitis C management and guidelines – February 3

Health Promotion and Disease Prevention

National HIV Testing Initiative: All promotional materials are available on the web, including logos, radio spots, fliers, snag bag inserts, and window decals. Orders are filled upon request. PRT staff participate in regular teleconferences for the HIV/STD/Hep C Listserv and the Viral Hepatitis Action Plan for IHS.

Native LGBT Proud Campaign: The campaign includes posters, fact sheets, and radio ads. Orders are filled upon request.

Tribal STD/HIV Policy Kit for Tribal Decision-makers: The Advocacy Kit is available on the IHS and NPAIHB website. Appx 250 hard copies and 300 jump drives with the kit have been distributed to date.

Native STAND Curricula: A culturally-appropriate, school-based healthy decision-making curriculum. PRT is working with the OHSU Center for Healthy Communities to recruit tribes to participate in the Native STAND dissemination project: http://oregonprc.org/projects/current/native-students-together-against-negative-decisions.html

Native VOICES: The Native VOICES mini-series generated over 102,745 video views on Facebook, reached over 259,150 people, and was clicked on, shared, liked, or commented on over 61,440 times!

Since its launch, the Native VOICES YouTube Channel has had 376 video views.

Website: 	The We R Native website launched on September 28, 2012: www.weRnative.org

The mobile site launched on September 28, 2013

| In March 2015, the site received: |  |
| --- | --- |
| Page views | 9,814 |
| Sessions | 2,937 |
| Percentage of new visitors | 74% |
| Average visit duration | 2:44 |
| Pages per visit | 3.34 |

- Over 350 health/wellness pages are on the website.

- We continue to work with INDIG to refine and improve the website, sitemap and wireframe:

    - Carried out website usability testing – In 2015

    - Redesigned the Homepage, Blog, and Videos sections – In 2014

    - Partnered with NativeThreads to offer additional Gear – In 2014.

    - Worked with the AdCouncil to embed rotating health Ads – In 2013.

Text Messages: The service currently has 2,577 active subscribers.

Twitter: Followers = 1,639

YouTube: http://www.youtube.com/user/wernative#p/f

The project currently has 263 uploaded videos, has had 24,401 video views, over 35,597 minutes of videos watched, and has 190 subscribers.

Facebook: http://www.facebook.com/pages/We-R-Native/247261648626123

By the end of the month, the page had 23,207 Likes.

Instagram: http://instagram.com/wernative

By the end of the month, the page had 845 followers.

Surveillance and Research

It’s Your Game Adaptation: All 15 participating tribal sites completed their IYG 12-month follow-up surveys. We continue to provide TA to 4 tribal ACF sites implementing Native IYG + parent-child components.

VOICES Adaptation: Data collection is complete for the study. All survey data has been entered and is now being analyzed.

Native LGBT-Two Spirit HIV Pilot Projects: PRT staff are coordinating pilot projects to test two potential Tech-Based HIV Prevention Interventions for adaption and/or use in Indian Country:

- Prevention/Screening: A pilot project is testing the effectiveness of text messaging to improve HIV knowledge, risk awareness, and STD/HIV screening practices among AI/AN youth 15-24, using the We R Native text messaging service. Data analysis is in progress (Activities coordinated by David Stephens).

- Treatment Adherence: A pilot project is testing the effectiveness of an App (iStayHealthy) to improve case management and treatment adherence for AI/AN PLWHA. (Activities coordinated by Jessica Leston)

STD/HIV Measures Project: The project is monitoring STD/HIV GPRA measures for IHS sites throughout Indian Country. Infographics are being generated to provide visual feedback data to all 66 IHS sites, 13 Urban sites and any tribal site that provides access.

Other Administrative Responsibilities

Publications

- Revised Chapter in a Book: Indigenous People and Mobile Technologies

- Health News and Notes: Native VOICES release

- Working on Native VOICES Adaptation paper

- Working on Native VOICES Outcomes paper

- Working on Texting 4 Sexual Health papers (x3)

- Submitted Native IYG Adaptation paper

Reports/Grants

- Submitted Honoring Nations Application – Was not awarded.

- IYG Quarterly Report

CDC Assignee

Jessica Marcinkevage, Epidemic Intelligence Service (EIS) Officer

TB cluster on Washington Reservation

- Prepared manuscript for submission to IHS Provider

  - Cleared through CDC Clearance

  - Approved through Portland Area IHS IRB

  - Pending approval from Tribal Health, Education and Wellness committee (expected: April 2015)

Diabetes-related hospitalizations among AI/AN in the Pacific Northwest

- Abstract accepted for presentation at EIS Conference (10-minute oral, April 20-24, Atlanta, GA), CSTE Annual Meeting (poster, June 12-16, Boston, MA) and American Diabetes Association (poster, June 5-9, Boston, MA)

  - Selected as a finalist for Robert Wood Johnson Foundation National Award for Outstanding Epidemiology Practice in Addressing Racial and Ethnic Disparities, CSTE Meeting

- Prepared dataset for modeling analysis, to identify risk factors for hospitalization

Public Inquiries

- We received a notice from a public health nurse at Nimiipuu regarding a pertussis case in a child who had attended the Tribal Head Start. They were working with state and county partners on the contact follow-up. She requested information on pertussis in WA and ID for inclusion in an article for the tribal newsletter, to raise awareness in the community. I was able to obtain information from ID from a colleague at the state’s public health department, and shared this with the nurse.

Partner/external agency meetings

- CDC Epi-Aid at University of Oregon: meningococcal vaccination campaign

- IHS General Data Mart Users Group Meeting

- Oregon Life Course Network meeting

- CSTE Tribal Epi Group Quarterly Call

- OHSU Faculty meetings

Epicenter Biostatitician

Nancy Bennett

Conference Calls:

- TPHEP conference planning calls weekly

  - Planning conference

  - Abstract review

- Immunization project

  - Webinar/call with Bryan at CHRIB to discuss NextGen query  SQL code

NPAIHB Meetings:

- Tribal Health Profiles meeting bi-monthly

  - Begin tribe specific reports

- Data meeting bi-monthly

  - Discuss THP report

  - Discuss Brfss data

  - Discuss immunization data

- Immunization project

  - Comparative analysis of GPRA data to RPMS data

  - Discuss possible sites for project

- Meeting with Jack Snowden to discuss MMO gaming applications

Miscellaneous

- Winter Grant writing workshop

- Immunization RPMS class

- Continue work on Tribal specific THP reports

Reports:

- Site specific THP

Injury Prevention Program

Bridget Canniff, Project Director

Luella Azule, Project Coordinator

Conference Calls

1/13, 2/17, 3/17 Econometrica  (IHS Evaluators:   Ciara Zachary, Monique Shepard, Mark Stewart,  IHS project officer, Celeste Davis, Bridget, Luella)

2/23, 3/24 TIPCAP Advisory Committee (Luella)

2/26, TIPCAP Administration (Bridget and Luella)

Meetings/Conferences:

2/6, 2/27, 3/17 IHS Project Officer meetings (Celeste Davis, Bridget and Luella)

Trainings/Webinars

1/14 Webinar:  Child Restraint Manufacturer What’s New Part 1, post CEU training to CPS Certification documentation, download powerpoint slides, complete webinar survey, watched YouTube:  Britax installation,

2/5 OHSU Taking a Native Stand for Indian Country-- Michelle Singer Lecture

2/20 Econometrica Webinar:  Child Passenger Seat from archive

2/24 Webinar:  Hot Topics Prescription Overdose

3/6 CPS checkup Oak Grove Fire station—Milwaukie

3/25 Webinar:  Addressing Health Disparities through the Nation Prevention Strategy & Partnerships:  The Role of Community and non-profits.

3/31 Social Media training

Technical Assistance & IP Resources:

Forward Grant Solutions Training and grant information to Ms. Fox, grant administrator

Update Contacts:   IP resource contacts

Forward IP grant information to Ms. Fox, and tribal contacts, CPS techs, IP coalition committee

Added relevant training materials to IP resources library

Forward Veteran Suicide from NB to Colbie

Review Hot Topics slides:  Naloxone distribution for Heroin OD  HYPERLINK "http://www.stopoverdose.org" www.stopoverdose.org)

January - March:  Core Activities  - Luella Azule

Made annual TIPCAP grantee meeting arrangements for June 2015

Plan for Econometrica April site visit

Reviewed & forwarded 16 IP-related announcements to CPS techs, Tribal IP Contacts and/or IP Coalition Committee

Maternal Child Health Projects:

Jodi Lapidus, Native CARS PI

Tam Lutz, PTOTS Project Director/Jr Investigator

Nicole Smith, MCH Biostatistician

Candice Jimenez, Research Assistant

Thomas Becker, Co-PI (TOTS to Tweens)

Native CARS Study

Goal of the Intervention Phase

The goal of the Native Children Always Ride Safe (Native CARS) project was to prevent early childhood vehicle collision morbidity and mortality in American Indian Alaskan Native children through the use of community base participatory model that incorporated tribal differences in cultural beliefs, family and community structure, geographic location, law enforcement and economic factors.

Objectives/Aims of Intervention Phase

We used qualitative research methods to identify community-specific concerns and barriers, and incorporate these findings into an effective behavioral change campaign. We disseminated these results widely, and worked with tribes to design tailored community interventions based on theoretical models of health behavior change. Finally, we assisted tribes as they implemented and evaluated the interventions through a controlled community trial.  During this five-year project we specifically aimed to:

- Determine the knowledge of AI community members about child passenger restraint systems, and determine barriers and facilitators that effect consistent and appropriate use in six tribes in the Northwestern US.

- Work with members of six Northwest tribes to determine effective methods to increase child safety seat use, developing tailored community intervention programs to address unique needs.

- Implement and evaluate the programs in the Northwest tribal communities, comparing improvement in child passenger restraint use to three comparison tribes in the Northwest through a controlled community trial.

Objective/Aims of Dissemination Phase

Because of the demonstrated success of the Native CARS Study, the study was award additional funds for a dissemination phase of the study, where the protocols, tools and intervention materials can be translated for use by other tribes both locally and nationally. These evidence-based tribal interventions will be adapted and disseminated via plans guided by a dissemination framework that leverages and expands upon tribal capacity built during the previous Native CARS cycle, by engaging the tribal participants as experts throughout this phase. Demonstrating the translation potential of Native CARS interventions into other tribal communities is an essential step toward reducing the disparity in motor vehicle injuries and fatalities experienced by American Indian and Alaska Native children in the United States.

During the current dissemination phase, we specifically aim to:

Develop the Native CARS Atlas (link to http://www.nativecars.org), a toolkit to assist tribes in implementing and evaluating evidence-based interventions to improve child passenger restraint use on or near tribal lands.

- Facilitate the use of the Native CARS Atlas (link to http://www.nativecars.org) in the six tribes that participated in the original initiative, to help sustain improvements in child passenger restraint use achieved during the intervention phase and provide lessons on use of the toolkit for other tribes.

- Use the Native CARS Atlas (link to http://www.nativecars.org) to assist at least 6 new tribes in the Northwest with demonstrated readiness to implement interventions to improve child passenger restraint use in their communities

Project News & Activities

This quarter the Native CARS Study continued with the developmental work of the dissemination phase of the study, meeting with contractors, working with tribal site content experts to draft, edit and finalize specific dissemination modules.    Three Native CARS group members reviewed presentations, spoke to local and organizational experts at the National Lifesavers conference in Chicago, IL.

PTOTS Study

.

- Specific Aim of PTOTS

The overall aim of this project is to test whether community and family-based interventions can alter feeding practices (breastfeeding, sugared beverage consumption, timing and type of introduction of solids, and influence parenting to reduce sedentary lifestyles (eg. limiting introduction of television/video viewing, encouraging development of motor skills and creating safe play opportunities) and whether such behavioral changes can impact childhood obesity and early childhood tooth decay.  The intervention framework is the social ecology model for health promotion that targets health behaviors at multiple levels.

TOT to Tweens Study

A staggering proportion, 3 of 4 American Indian/Alaska Native (AI/AN) children between the ages of 2-5, have experienced tooth decay, over two-thirds have untreated decay, and over half have severe tooth decay. While this may politely be referred to as a "health disparity," it could more aptly be termed a "health disaster." Many AI/AN children experience tooth decay before the age of two. Tooth decay in that age group leads to further tooth decay and other oral health problems later in childhood.

The newly funded TOTS to TWEENS is a follow up study to The TOTS Study (Toddler Obesity and Tooth Decay) Study) an early childhood obesity and tooth decay prevention program. The goal of this study is to survey and conduct dental screenings with the original group of toddlers to test whether interventions delivered in the TOTS will influence the prevalence tooth decay in older children.  Through qualitative approaches, the study will also assess current community, environmental and familial factors that can influence oral health in children to understand any maintenance of preventive behaviors over the last ten years within the entire family.

The TOTS to Tween Study is administered through the NW NARCH program at the NPAIHB.   The TOTS to TWEENS Study will be led by Co-Principal Investigators, Thomas Becker, MD, PhD and  Tam Lutz, MPH, MHA.

For more information about the TOTS to Tweens Study, contact Tam Lutz at tlutz@npaihb.org

BOARD ACTIVITIES

Program Support or Technical Assistance

- BRFSS technical support

- Provide reporting to NARCH program on past NARCH activities, Jan-Feb (Tam, Nicole)

- Coquille BRFSS technical support/meetings, Mar (Nicole)

- Edit/revise Cow Creek BRFSS paper, Mar (Nicole)

- Food Donation Requests for Indian Day, Jan- Mar (Candice)

- Wellness Presentation Review,  (Candice)

PTOTS and TOTS to Tweens

Program Support or Technical Assistance

- Website final edits for NPAIHB section on TOTS to Tweens (Candice)

- Created intro packets for delegates and distributed the at QBM (Tam)

- Created needed document for HR for hire of Temp to help with launch (Tam)

- Created needed document for HR for hire of Temp to help with launch (Tam)

- Compressed ‘Dental Caries Exam Manual’ for email usage (Candice)

- Compiled latest contract templates (Candice)

- Literature research on Oral Health Questionnaire/Surveys (Candice)

- Created overall project, tribal & protocol specific timelines (Julia)

- Compiled contact sheets (Julia)

- Begin development of staff contracts (Julia)

- Literature search for youth dental health programs (Julia)

- Begin communication for possible logo development for study (Candice)

- Updated staff information for TOTS to Tweens on NPAIHB website (Candice)

- Continued development of staff contracts (Tam, Julia, Candice)

- Created Recruitment Script and Community Announcement (Julia)

- Reviewed documentation need for IRB (Tam)

- Drafted Recruitment document for IRB (Tam)

- Edited timeline, recruitment script, community announcement and consent form (Tam)

- Sent first contact packet to all six tribes (Tam)

- Review relevant literature, measurement protocols for WHO protocol and PUFAS, Food frequency questionnaires (Tam)

- Wrote/Updated Confidentiality Training for Site Coordinators (Julia)

- Drafted Child Informed Consent and Parent/Caregiver KAB forms (Julia)

- Developed Tribal Commitment project timeline (Julia)

- Literature search for youth dental health programs (Julia)

- Communication with contractor for study logo (Candice)

- Revised contracts for investigators (Tam)

- Completed examiner contracts (Tam, Julia, Candice)

- Completed Practicum paperwork for KAB survey development (Tam, Candice)

- Website content shared to OHSU PRC for latest project information (Candice)

CARS

Meetings - Conference Calls – Presentations – Trainings

- Site Coordinator Conference Call – January-Mar (Tam, Candice)

- Individual Site Coordinator Meetings via Phone (Tam, Candice)

- Meeting with KAT Communications – Feb-Mar (Jodi, Tam, Nicole, Candice)

- QBM for presentation on Native CARS Dissemination phase – Jan (Tam, Nicole)

- Website webinar with potential contractor – Mar (Jodi, Tam, Nicole, Candice)

- NHTSA Lifesavers Conference – Chicago, IL – March 13-14 (Tam, Nicole, Iola)

- Media meeting with ED, Mar (Tam, Jodi)

Program Support or Technical Assistance

- QBM Presentation Preparation – Jan (Tam, Nicole, Candice)

- Module 2 communication with site coordinator for updates, Jan-Mar (Candice)

- Module 4: Draft and test Epi Info database, Feb-Mar (Nicole)

- Module 5 – Draft, Jan-Mar (Nicole, Candice)

- Module 5 – Editing, Jan (Tam)

- Module 5: Draft intervention plan templates, Feb-Mar (Candice)

- Website Design Feedback to KAT, Jan (Nicole, Candice)

- Module 6 – Review/Revise, Jan (Tam, Nicole, Candice)

- Module 6: Media-linked the module to specific files (Candice)

- Module 7: Health Education new outline draft (Candice, Tam)

- Module 9 – Review/Revise, Jan-Mar (Tam)

- Module 9: Review latest KAT edits in ‘Other Policy’ section (Tam, Candice)

- Module 9: Gathered ID hospital information regarding car seat policies with Crissy (Candice)

- Registration and travel preparation for Lifesavers Conference, Jan-Mar (Candice)

- Travel arrangements for QBM for staff and site coordinators, Jan (Candice)

- Scheduling of AdobeConnect session with KAT, Jan-Mar (Candice)

- Completed ordering for toolkit and promotional materials for dissemination, Feb (Candice)

- Wrote and edited KIM abstract for submission, Feb (Nicole)

- Module 9: Review latest KAT edits in ‘Other Policy’ section, Feb (Candice)

- Completed contract amendment for Rebecca Hunt, Feb (Candice)

Travel

- NHTSA Lifesavers Conference – Chicago, IL – March 13-14 (Tam, Nicole, Iola)

Medical Epidemiologist

Thomas Weiser, Epidemiologist (IHS)

Projects:

*One Key Question

*Tobacco Cessation in Pregnancy

*HIV/AIDS/HCV/STI Clinical Training

*Improvement Support Team

*EIS Supervision

*Tribal Community Health Profiles

*Adult Immunization Improvement Project

*HPV Improvement Project

*National Data Warehouse Data Validation/EIS Surveillance Project

*Childhood Immunization Coverage, Portland Area

Opportunities:

*Attended learning session and follow-up meeting with OHA for the Tobacco Cessation in Pregnancy Project.

*NWAETC provided clinical training at NPAIHB, March 18-19, 2015 with a good turnout for the class.

*NPAIHB is developing a data registry for internal use and including specifications for which data can be requested for outside users.

*Successfully confirmed 3 of 8 sites to participate for the Adult Immunization Composite Measure Evaluation Project. Working on IRB submissions to Phoenix and Great Plains Areas and completing a resource guide to help sites focus on quality improvement activities for adult immunizations.

Meetings/Conference Calls:

Meetings:  NPAIHB Regional Diabetes Meeting

OR Emergency Planning Meeting

Portland Area IPC/QILN meeting

Immunization Package Training

Cow Creek Clinic Site Visit

CSTE Tribal Epi Workgroup

Infant Mortality Collaborative

IPC Learning Sessions

NWAETC HIV/HCV/STI Clinical Training

National and Portland Area Immunization Coordinators call

Northwest Native American Research Center for Health (NARCH)

Tom Becker, PI

Victoria Warren-Mears, Director

Tom Weiser, Medical Epidemiologist

Tanya Firemoon

Tasha Zaback

Consultants:  multiple

This report covers activities related to NARCH 6 and 7.  NARCH 6 is operating on carry-forward funds, while NARCH 7 is in the second year of funding.

The Summer Research Training Institute planning is complete, and we are awaiting the arrival of over 100 tribal guests from around the country.  Our last effort was the 11th such effort sponsored by the Board, with input from OHSU faculty and staff, as well as a host of consultants…so the upcoming event will be our 12th  anniversary offering.  We were successful in filling up our course instructors and our student enrollment in just a few weeks—Ms. Zaback did a masterful job at getting the advertisements around the country. As earlier reported, we will try a a new course this year, in ‘risky business’ and healthy decision making, under the guidance of Stephanie Rushing, PhD, and Michelle Singer of OHSU. We hosted another out of phase course this past January.  Evaluations were consistently positive for that course, focused on grant writing.

Ms. Zaback has established hotel contracts for 2015, and we expect to award travel scholarships again this summer to around 80 trainees.

Also under NARCH funding, we recruited additional fellows who will receive small scholarships to help advance their careers in Indian health.   Our scholarship program continues to graduate new researchers, and seems to be successful overall.  We have added two new fellows who will receive partial scholarships, and one new fellow who will receive a full scholarship under the NARCH program.  Ms. Firemoon has been extremely helpful in watching over this part of the NARCH, and her efforts to help the summer program have also been very valuable.

The 7th funding cycle for NARCH.  This grant has substantial overlap with the NARCH 6 program with the emphasis on training.  The 8th cycle of NARCH funding was announced in the spring and we are working with those funds to understand more about possible long term effects of a toddler tooth decay prevention program that we conducted ten years ago.

To date, the NARCH funding stream has brought in approximately $12 million to the Board to address health issues among tribal people in the Northwest and beyond. We are very pleased that the federal government continues to find funds to run this program. At the federal level, Drs. Clif Poudry (Seneca, now retired from the federal program at NIH), Alan Trachtenberg, Mose Herne (Seneca), John Mosely Hayes, and Sheila Caldwell have been instrumental in finding federal funds to advance the health of tribal people in this national program.

Northwest Tribal Comprehensive Cancer Control Project

Kerri Lopez, Director

Eric Vinson, Project Specialist

Special projects

- April 22, 2015 Northwest Tribal Clinical Cancer Update – April 22

  - Follow-up calls for recruitment; Portland Area Clinical Directors – 35 registered

  - Gathering necessary documents for CEU credits – Legacy sponsor

- Comprehensive Cancer Coalition Meeting – April 21

  - Follow up recruitment – 25 registered

  - Travel reimbursement forms prepared

- Northwest Tribal Cancer Action Plan Implementation Funding

  - 2 Application received and funded

  - 12 funded to date

  - Follow-up recruitment of applications continues

- June 25th Cancer Risky Business – Warm Springs

  - Hotel Logistics completed

  - Recruitment save the date flyer/agenda competed and disseminated

  - Planning meeting held March 25th

- Oregon Comprehensive CCRS’s Tribal and Rural Advisory Board

  - HPV project selected as cross cutting project

  - Will work on creating job description – HPV focus groups

- Discussion with state MCH partners for looking a AI/AN pregnant women who smoke

  - GPRA numbers, quit line information, three tribes see pregnant women

- National Network Partnership

  - Attended face to face meeting Traverse Michigan – January 13-15th

  - Editing rough draft presentation for Tribes in the state regarding E-Cigarettes

  - Editing YR 2 work-plan for The National Native Network

  - Familiarized with Change Tool Summary Report, RFA Materials for TPEP, Tobacco and Diabetes Program Integration in Oregon’s Tribal Communities, NNN work plan and NNN subcontract

  - Developed detailed scope of work for contract

  - Developed project presentation for NNN partnership meeting

  - National Native Network Technical Assistance Webinar; Evaluation Planning Facilitation 3/12

  - National Native Network Technical Assistance Webinar; Cancer Risk Reduction in Indian Country

- Social Media Class Training;

- Led Wellness activities for a week 1/20-1/23

- Attended meeting with OHA healthy communities – discussion on in person training and scope of work for contract

- Preliminary work on updating Tribal Tobacco Policy workbook

- Clinical Tobacco Cessation Training – March 12 & 13

  - 14 participants from 9 NPAIHB Member Tribes, 2 NPAIHB Staff

- AIMS manuscript publication paper

  - Revised draft received from FHCRC – submit to IRB

- BRFSS progress

  - Tribe 5 – presentation on brfss / tribal resolution passed

    - Working on IRB / Tribal questionnaire

    - Tribe 4 -BRFSS power point presentation –  done

  - Tribe 3 ––power point presentation done

  - Tribe 2 – frequencies updated, summary report complete – all data sent to tribe

- Cancer Data Fact Sheet Update – Ongoing

  - Positive response from Oregon and Idaho Cancer Registries

- HPV Roundtable meeting follow-up – 65 organizations invited

  - Chose national campaign workgroup

  - Focus on promoting hpv vaccination – target 11-12

  - CDC education campaign rollout in June

  - Travel reimbursement received

  - CDC Cancer Survivorship grant application - decision to not apply due to cancer registry requirements

- Connected with Oregon BRFSS oversample regarding survivorship questions

- GPRA Measures – Data Committee Discussion of GPRA

- Tobacco Cessation Quit line article

  - Disseminated to state quit line managers for further discussion of quit line efficacy

- CDC Success stories website troubleshot through email with creator

- June 3&4 Cancer Survivorship Conference in Everett, Washington

  - dissemination and registration

Technical assistance via telephone/email (125 calls to NW tribes)

- Contacted all NW tribes – recruiting for mini grants

  - Follow up for ta with tribes for ta

- Recruitment for clinical update

- Recruitment for coalition meeting

- Recruitment and registration for Cancer Risky Business

Meetings/Conferences

- American Association for Cancer Education Interim Meeting

- Oregon Tobacco Grantee Grant application training and Tribal Tobacco Meeting in Klamath Falls

- Diabetes and Cancer Projects Staff meeting

- NPAIHB advice on AIAN health surveillance improvement OR BRFSS oversampling

- Northwest conference meetings (4)

- PRC – rural/tribal advisory board meeting

Conference calls

- Webinar – CDC “Success Stories”

- Webinar – “Patient-Centric Technology and the Consumerization of Healthcare”

- Webinar – GWU “Aligning State Cancer Plans with National Priorities”

- Conference Call for CDC Tribal Cancer Project Directors and CDC Project (3)

- Oregon Tribal Tobacco Prevention and Education Program; Grantee Capacity Advisory Group Conference Call

- BRFSS call

- Knight Community Cancer Grant call

- Cancer Plan Tools Webinar

- American Association for Cancer Education Executive Council call

- National Native Network workplan call (3)- Web Indigenous Health in Context

- GWU Cancer Technical Assistance Advisory Board call

Northwest Tribal Dental Support Center

Joe Finkbonner, Executive Director

Ticey Casey, Project Manager

Bonnie Bruerd, Prevention Consultant

Bruce Johnson, Clinical Consultant

Kathy Phipps, Epidemiology Consultant

The overall goal of NTDSC is to address the broad challenges and opportunities associated with the 35 IHS and Tribal dental programs utilizing the combined resources and infrastructure of IHS Headquarters and IHS Portland Area, indirectly improving the oral health of the Native American people in the Pacific Northwest.  NTDSC activities are listed in categories corresponding to the current grant objectives.

Provide clinical and preventive program support.

- NTDSC consultants completed a site visit to the Chemawa Dental Program in January, completing both clinical and prevention site visits, including reports, at 6 Portland Area dental programs this fiscal year, meeting the yearly objective. NTDSC has exceeded this objective yearly during this grant cycle..

- NTDSC developed a format to assist programs in developing a formal Quality Improvement Project. During the Area Dental Meeting, dental staff participated in an activity to develop QI objectives. This objective has been met for this grant period.

- NTDSC staff and consultants have been working in collaboration with WA Dental Services Foundation (Delta Dental) to meet some identified mutual objectives. Seven dental programs are participating in the "Baby Teeth Matter" program that is aimed at increasing dental access for 0-5 year olds and reducing the number of children referred for dental work under general anesthesia. This program includes data collection, face to face and webinar meetings, and ongoing program evaluation. Data from the first year show a large increase in dental access for 0-5 year olds at the 7 dental programs participating in this project.

- Portland Area met all 3 dental GPRA objectives this past year.

- NTDSC provides technical assistance to all Portland Area dental programs as appropriate.

Implement an Area-wide surveillance system to track oral health status

- Portland Area completed the Basic Screening Survey for 1-5 year olds this fall, collecting survey data from 18 clinics for 1,308 1-5 year olds. The results of these surveys have not been released by IHS HQ yet.

Provide continuing dental education opportunities

- Dental staff completed the “Update on Prevention” course for 2 CDEs during site visits.

- NTDSC is currently planning the annual dental meeting July 28-29, 2015 at Tulalip Resort. After this meeting, there will be additional sessions for Dental Directors and Baby Teeth Matter participants.

Work with IHS Headquarters and other Dental Support Centers towards meeting national HP/DP objectives.

- NTDSC Prevention Consultant serves as the Portland Area dental representative on the national HP/DP Committee.

- NTDSC Prevention Consultant serves as Co-Chair of the national Early Childhood Caries Collaborative but resigned as of March 2015. Dr. Bruerd was co-presenter at a session January 28th for Combined Councils.

- NTDSC consultants participate in email correspondence, national conference calls, and respond to all requests for input on national issues.

Northwest Tribal Registry Project-Improving Data and Enhancing Access (IDEA)

Victoria Warren-Mears, P.I.

Sujata Joshi, Project Director

Kristyn Bigback, Project Support Specialist/Biostatistician

Jenine Dankovchik, Biostatistician

Project news and activities

Jenine Dankovchik, who has worked with IDEA-NW since January 2011, transitioned into her new position as WEAVE Evaluation Specialist within the EpiCenter. We are grateful for all of Jenine’s work on this project, and wish her the best in her new position. Jenine continued to assist IDEA-NW in wrapping up a few projects, including the Washington trauma manuscript and the health data literacy training.

We completed several linkages this quarter, notably our linkages with Washington and Oregon birth, fetal death, and death certificates. These data will allow us to begin work on several planned Maternal and Child Health (MCH) analyses. We completed linkages with Oregon and Washington hospital discharge records and the Cancer Data Registry of Idaho. We are working on cleaning and coding the datasets we received after these linkages, and will use these data for CHSDA-level tribal health profiles and data requests from Tribes.

After several months of re-analyzing data and re-writing our findings, the manuscript “Uncovering a Missing Demographic in Trauma Registries: Epidemiology of Trauma among American Indians and Alaska Natives in Washington State” was accepted to the journal Injury Prevention for publication. Our manuscript on misclassification in Oregon and Washington hospital discharge data was provisionally accepted to the journal Health Services Research.

Current status of data linkage, analysis, and partnership activities

- Northwest Tribal Registry (NTR) data linkages

- Completed linkage and double review of 2012-2013 Washington hospital discharge (CHARS) records

- Linkages with Washington birth certificates (1997-2013)

  - Completed double review for linkage with mother IDs

  - Completed linkage with father IDs

  - Combined results and sent final match file and certificate of data destruction to Washington Dept. of Health (DOH)

- Completed double review for linkage with Washington death certificates (2011-2013), sent results and linkage summary to Washington DOH

- Completed linkage with Oregon hospital discharge records (2012-2013)

- Completed linkage with Cancer Data Registry of Idaho, 1992-2012

- Completed linkages with Oregon vital statistics

  - Oregon birth certificates, 1997-2013 (link with mother and father IDs)

  - Oregon death certificates, 1997-2005, 2013

  - Oregon fetal deaths, 1997-2013 ( link with mother and father IDs)

- Tribal Health Profiles (THP) project

  - Idaho, Oregon, and Washington State THPs

    - Mailed copies of THP reports to Tribes and other partners

    - Made minor corrections and sent THP reports for reprinting

  - CHSDA THPs

    - Worked on indicators for Umatilla THP

      - Completed cancer, hospital discharge, demographic, environmental health, and GPRA indicators

      - Requested and received OR and WA BRFSS data, and began work on BRFSS indicators

      - Worked on re-running mortality indicators

      - Input figures into InDesign template, worked on updating text

    - Began work on indicators for Colville THP

- Cancer Registry Data and Cancer Fact Sheets

  - Cleaned, coded and merged ID, OR & WA cancer registry data to create a three-state cancer dataset; updated data dictionary and READ ME document

  - Calculated misclassification and pre/post-linkage rates for Idaho, sent linkage report to data manager

  - Re-ran numbers and completed state and area cancer data fact sheets (2008-2012); sent to cancer registrars for review

  - Started work on Umatilla CHSDA cancer fact sheet

- Hospital discharge data

  - Addressed final round of comments for Health Services Research manuscript, and resubmitted to journal editors

  - Completed cleaning and coding Oregon hospital discharge and Washington CHARS data; merged with previous years’ data; completed data dictionaries for both datasets

  - Sent linkage summary reports to Oregon and Washington data managers

  - Ran pre vs. post-linkage rates and rate ratios for OR and WA data (2012-2013)

  - Worked on preparing and analyzing data for fact sheet on potentially avoidable hospitalizations

- Death Certificate Data

  - Cleaned and coded Washington death certificate data (2011-2013); merged new records into 3-state death certificate dataset; updated data dictionary and READ ME document

- Washington Trauma Data

  - Revised Washington trauma manuscript.  All analyses were re-run after determining that the data set contained duplicates which were not identified as such.

- Health Data Literacy Training

  - Completed a draft of the health data literacy training (five modules), and began working on PowerPoint slides for training

  - Developed a Health Data Literacy Cheat Sheet that describes common statistical concepts and tools

- Data requests/Technical assistance

  - Looked into oral health-related hospitalizations and other oral health access indicators for Jim R.

  - Nez Perce Cancer Data – ran additional comparisons of cancer incidence rates (Nez Perce AI/AN vs. all other AI/AN in Idaho) and sent to Tribe

  - Provided suicide hospitalization and mortality numbers to THRIVE Project, discussed developing a suicide data fact sheet with Colbie

  - Provided population estimates (AI/AN teens ages 11-14) to Project Red Talon for grant application

  - Provided chart showing domestic violence screening rates (GPRA measure) to Ryan for grant application

  - Provided Elizabeth Knaster (UIHI) with a summary of linkages, misclassification results, and products that used data from linkages with NTR11

- Other data-related activities and products

  - Created new population denominator file (1990-2013) and updated READ ME document

  - Worked on testing methods for conducting linkage double reviews and running kappa analyses; developed a “How To” methods document describing the double review process

- Grant Administration and Reporting

  - Completed Office of Minority Health (OMH) PDS report for Year 3 Quarter 2

- Collaborations with other programs and other activities

  - Completed trainings for maintaining EpiDataMart Access

  - Finalized 6-month post-internship evaluation survey

  - Worked on creating data center for internal use and for website

    - Sent proposal describing website content and structure to Jim Fry

    - Started internal/external data resources inventory

    - Created and organized Data Center content in EpiShare Drive

  - Worked on tribal epidemiology presentation for PSU class

Data dissemination

- Mailed State THPs reports to tribal health directors, tribal clinic directors, tribal councils, and other partners

- Wrote article on life tables manuscript for January Health News & Notes newsletter

- Manuscript “Uncovering a Missing Demographic in Trauma Registries: Epidemiology of Trauma among American Indians and Alaska Natives in Washington State” accepted to Injury Prevention for publication

Travel

Linkages

- Oregon Hospital Discharge, Salem, OR					1/15, 2/5

- Cancer Data Registry of Idaho, Boise, ID					3/5

- Oregon Vital Statistics, Portland, OR						3/24, 3/26

Other Meetings, Calls and Trainings

- Call with Office of Minority Health Evaluation Team				1/9

- OHSU seminar on Probabilistic Linkage for Injury and Violence Research 		2/9

- Chronic Disease Evaluation Webinar						2/19

- Meeting with Colbie to discuss suicide data					2/23

- CSTE Tribal Epidemiology Workgroup call					3/3

- MCH Graduate Student Epidemiology Program  Welcome Call 			3/4

- CSTE Tribal Epi Manuscript Workgroup call					3/10

- Data Literacy Training planning meeting 					3/12

- Meeting with NPAIHB web developers 						3/16

- Call with Liz Knaster (UIHI)  re: next steps with UIHOs 				3/17

- Cultural Exchange with Maori delegation					3/20

- Social Media Training								3/30, 3/31

THRIVE (Tribal Health: Reaching out InVolves Everyone)

Colbie Caughlan, Project Manager

Celena McCray, Project Assistant

Site Visits

Tribal Site Visits

- Chehalis Tribe, NPAIHB QBM, Ground Mound, WA, January 20-21

- Cowlitz Tribe, QPR Training, Vancouver, WA, January 27

- Cowlitz Tribe, QPR Training, Longview, WA, January 28

- Yakama Nation, GLS Grant Partnership meeting, Heritage University, Toppenish, WA, February 12

- Coeur d’Alene Tribe, Zero Suicide Training, Plummer, ID, February 18-20

- Kalispel Tribe, Eastern WA Tribes Suicide Prevention Summit, Airway Heights, WA, February 23-26

Technical Assistance & Training

During the quarter, project staff:

- Participated in 32 meetings and conference calls with program partners.

- Solicited feedback from Native youth in the region about updating THRIVE’s suicide prevention media campaign.

- Met with the OHSU facilitator and emailed with partners of the 2015 THRIVE Conference for Native youth. Registration will open April 8 for the conference.

- Assisted Tribes in Eastern WA with hosting their suicide prevention summit February 2015.

- Participated in three webinars.

During the quarter, THRIVE provided or participated in the following presentations and trainings:

- THRIVE Presentation at the NPAIHB QBM, 70 attendees – Grand Mound, WA, Jan. 21st

- BOLI Supervisor’s Training 1, project manager – Portland, OR, Jan. 26th

- QPR Facilitation for the Cowlitz Tribe’s Vancouver site, 12 attendees – Vancouver, WA, Jan. 27th

- QPR Facilitation for the Cowlitz Tribe, 20 attendees, morning session – Longview, WA, Jan. 28th

- QPR Facilitation for the Cowlitz Tribe, 12 attendees, afternoon session – Longview, WA, Jan. 28th

- THRIVE Suicide and Bullying Prevention Presentation and booth at the NERDS 2nd Annual Youth Gathering, 18+ attendees – Jackson, CA, Feb. 8th

- Zero Suicide training at the Coeur d’Alene Tribe – Plummer, ID, Feb. 19-20th

- BOLI Supervisor’s Training 2, project manager – Portland, OR, Feb. 23rd

- QPR training for trainers, project assistant – Spokane, WA, Feb. 24th

- Presentation at the Eastern WA Tribes Suicide Prevention Summit, 42 attendees – Spokane, WA, Feb. 25th

- THRIVE Suicide and Bullying Prevention Presentation and solicit feedback for suicide prevention campaign, 300 attendees – Chemawa Indian School, Salem, OR, Mar. 16th

- ASIST training for trainers, project assistant – Medford, OR, Mar. 22-26th

- Social Marketing and THRIVE Presentation at the University of Oklahoma’s annual Native Men and Women’s Wellness Conference, 25 attendees – San Diego, CA, March 24th

During the quarter, the MSPI project responded to 153 phone or email requests for suicide, bullying, or media campaign-related technical assistance, trainings, or presentations.

Health Promotion and Disease Prevention

THRIVE Media Campaign: All THRIVE promotional materials are available on the web. Materials include: a logo, three community murals, posters, fact sheet, t-shirts, note pads, and window decals.

During the quarter, THRIVE solicited feedback from Native youth audiences for the updated campaign. The campaign will include posters, rack cards, tip cards, and a radio public service announcement. Each of the 43-federally recognized Tribes in the Northwest will automatically be sent a box of these materials to use in their communities when the materials are ready for dissemination in mid-2015.

Other Administrative Responsibilities

Publications

- Article in NPAIHB January 2015 Quarterly Health News and Notes

Reports/Grants

- Submitted MSPI year 6 semi-annual report, March 31

- Submitted SAMHSA’s Garrett Lee Smith youth suicide prevention year 2 continuation grant, March 2

Wellness for Every American Indian to View and Achieve Health Equity (WEAVE)

Victoria Warren-Mears, Principal Investigator

Jessica Marcinkevage, Epidemiologist

Jenine Dankovchik, Evaluation Coordinator

Nora Alexander, Health Educator/Communication Spec.

Birdie Wermy, National Evaluation Specialist

Staff Updates January – March 2015

- All hiring for WEAVE-NW positions is now complete – February

Sub-Awardees

- Reviewed six applications and provided feedback

- Revised applications will be submitted to PGO for approval by March 3rd

- Another series of revisions were completed on the applications and they were submitted to PGO for approval; waiting to hear their decision (all)

Grant Administration and Reporting

- Began work on submitting grant report due in March

- Annual Progress Report and Year 2 Plan was submitted to CDC on March 18th  (VWM, JM)

Evaluation

- Began work on database to collect internal process evaluation data

- Continued work on process database (JD)

Training and Health Education

- Began discussions with Risky Business and NIKE Native Fitness planning groups

- Met with other projects to plan Risky Business training which will be in June (JM, JD, NA)

- Began research for Risky Business nutrition presentation (NA)

- Worked on curriculum for data literacy training which will be sometime late summer (JD)

- Began researching tribal public health policy for library (NA, JD)

- Met with Dan & Tim Gilbert from CTUIR regarding work group, work plan, project objectives & goals.

- Met with Karen Cook, Lindsey & Becky from CTUIR regarding project CHA.

Collaborations with other programs/other

- Working with IDEA-NW on data literacy training

- Working with NTCCP and WTDP on Risky Business training

- Provided data for DHAT grant application

- Cultural Exchange with Maori visitors

- Met with workgroup & other organizations supporting CTUIR in this project collaboration, VWM shared information regarding Project ECHO

Travel

Site Visits

- WEAVE Site Visit @ St. Anthony Hospital & CTUIR – 3/13

Meetings/Calls/Trainings

- GHWIC All-Hands Programmatic call (VWM, JM, BW, NA)			2/5

- WEAVE internal staff meeting (VWM, JM, BW, NA, JD)				2/5

- WEAVE meeting with CDC Project Officer (VWM, JM)				2/9

- WEAVE internal evaluation planning meeting (BW, JD)				2/12

- WEAVE internal staff meeting ( JM, BW, NA, JD)					2/12

- WEAVE meeting with CDC Project Officer (VWM, JM)				2/17

- GHWIC Evaluation monthly call (JD, BW)						2/18

- GHWIC Component 2 grantees call (VWM, JM, BW, NA)				2/19

- Chronic Disease Evaluation Webinar (JD)					2/19

- WEAVE internal staff meeting (VWM, JM, BW, NA, JD)				2/19

- Meeting to discuss NIKE Native Fitness (JD, NA, Erik Kakuska)			2/26

- WEAVE internal staff meeting (JM, BW, NA, JD)					2/26

- Data Meetings (JD)								Ongoing

- NPAIHB Staff Meeting (All)							3/2

- GHWIC All-Hands Programmatic call (VWM, JM, BW, NA)			3/5

- WEAVE internal staff meeting (VWM, JM, BW, NA)				3/5

- RWJF Webinar: Strengthening the Commitment	(NA)				3/6

- WEAVE Monthly Call with CDC Project Officer (VWM, JM)			3/9

- Planning meeting for data literacy training (JD)					3/12

- WEAVE internal staff meeting (VWM, JM, BW, NA)				3/12

- WEAVE internal staff meeting – data lit training catch up (JD, NA)		3/13

- WEAVE site visit @ CTUIR (VWM & BW)						3/13

- GHWIC Performance Measures Workgroup (VWM)				3/16

- Website meeting (NA, JM)							3/16

- WEAVE problem solving meeting with CDC Project Officers (VWM, JM)		3/16

- WEAVE internal staff meeting – sub-awardee applications (NA, JM)		3/17

- WEAVE internal staff meeting (VWM, JM, BW, NA)				3/19

- Chronic Disease Evaluation Webinar (JD)					3/19

- Planning meeting for Risky Business (JD, JM, NA)					3/25

- WEAVE internal staff meeting (JD, JM, NA)					3/27

- Cultural exchange with Maori visitors (VWM, JM, NA, BW)			3/20

- Social Media Basics training (NA, BW)						3/30

- NCCOR Connect & Explore Webinar (NA)					3/31

- Tribal Farm to School Webinar (NA)						3/31

- Data Meetings (JD, JM)								Ongoing

Challenges and Opportunities

Sub-awardee applications have taken longer to approve than expected due to lengthy approval process by funding agency.

Western Tribal Diabetes Project

Kerri Lopez, Director

Don Head, Project Specialist

Erik Kakuska, Project Specialist

- Trainings:

- DMS Training at NPAIHB:  12/2—12/4

  - 11 participants:  3  from Portland area tribes 8 out of area

- DMS Training – September 23-26th

  - 16 participants 7 NW tribes – 7 Out of area

- Chronic disease module @Cancer coalition meeting

  - 35 participants - Chair aerobics session

  - Invites to Siletz and Coos for entire module

- Technical Assistance via telephone/email

- Chapa De:,TA  information on the DMS Trainings that we offered

- Chehalis,  ta on the audit

- Cow Creek, ta for mailing labels from RPMS; screenshot for RPMS,  PCC Management Reports menu; security keys for the package, dm conference;  DSM Education; QMAN search; entering historical information is probably easier through DMU, than through EHR,

- Gerald L. Ignace Indian Health Center:  ta Gen, TA reports, finding a report  DM patients that do not have a primary care provider

- Lummi, request for the HSR results for clinic.

- Quinault, ta for the security key (BDMZ REGISTER MAINTENANCE) needed from the site manager in order to access this function of DMS

- Siletz, ta  audits from the previous three years off of the Web Audit and the HSR

- Squaxin Island, ta  how to print out Individual Audit sheets, and I walked her through the process of printing them out for her entire register

- Tulalip,  requested the Excel files for the HSR, and CC’d the THD

- DMS confirmation emails sent for trainings

- Worked with 3 tribal programs on year end reports

- Special Projects

- NW Regional Diabetes Conference flyers finalized Scheduled for January 22-23, 2015

  - Dr. Bullock confirmed for NW conference

  - Registration and agenda

  - 60 attendees registered – Confirmation sent to all registered

  - Working on break out and panel sessions

  - Working on needs from tribes for poster board session

  - Developed the guidelines for poster board presentations for the Northwest Diabetes Regional Conference

  - Developing poster board work sheet

  - Meeting with TLDC representative – finalize agenda

  - Working with Elaine on logistics

  - Outreach and recruitment to  all  NW Tribes for participation

  - Various calls to DM coordinators/specialist – SDPI

  - Created official invitation letters to Round Table panelist

  - Follow up will all NW tribes by phone, email who have not yet registered

- WTDP Year-end Report

  - FSR, narrative, best practices

  - Gathered training, key measures, for report

- Epi Year-end report –

  - Trainings, committees, tribal activities

  - Gathered data for Project Director’s portion of the Epicenter Report

- Hiring committee for new CDC grant: health educator

  - Applicant screening meeting - matrix

  - 3 interviews complete

- Hiring committee for new CDC grant: evaluator

  - Screened – did matrix

  - 5 interviews

  - 2 positions offered

- Orientation new project assistant

  - Set up office space, computer, phone, etc. – electronic files

  - WTDP database

  - The Diabetes Screening Toolkit

  - Siletz Health Status Report/IHS website

- Diabetes charities of America, federal campaign

  - Updated training grid

  - Sent 990

- Submitted SOW for NF Xll – Indian Health Service

- Reserved at Nike Campus TWC – August 16-18th 2015

- Submitted SOW for diabetes regional meeting – Indian Health Service

- Printed, bound, and mailed all the HSR reports to the clinics that submitted the audit, NPAIHB delegate, DM Coordinators, and THDs

- Native Fitness XI

  - Mailed multiple Certificate to attendees

  - Invoice follow-up

  - Supplies - ES

- 9th annual Dancing in the Square Powwow

  - Meeting, loading and clean up

  - Van rental

- Preventing Harassment in the workplace

- HIPPA training

- Reviewed and updated the website for current and correct information for our trainings, and our tools and publications

- Knight Grant proofreading

- Office Depot orders (including end of year calendar order and consolidation)

- Pendleton order

- DMS computer time – training

Meetings/Conferences

- OHA – new contract negotiation

- Trainings:

- DMS Training (7 participants, 4 from NW tribes, 3 out of area)

- Follow-up, including entering evaluations into survey monkey

- DMS Training in Aberdeen, South Dakota (15 participants)

- Site Visits

- Lower Elwha

- Registry clean-up by utilizing various reports; GEN, QMAN, LMR, TU15

- 2015 Annual Audit

- Skokomish

- Registry clean-up by utilizing various reports; GEN, QMAN, LMR, TU15

- 2015 Annual Report

- Squaxin Island

- 2015 Annual Report

- Quinault (Ocean Shores) Register clean-up by utilizing various reports; GEN, QMAN, LMR, TU15; 2015 Annual Audit

- Makah (Neah Bay)  Register clean-up; 2015 Annual Audit

- Siletz:  GEN, QMAN, LMR, DM Audit, TU14; ta provided  to wellness coordinators – strategies to increase community involvement

- Special Projects

- SDPI mid-year report – training numbers, best practices

- Northwest Tribal Diabetes Conference January 21-23rd , 2015

  - 76 NW tribal programs attended conference

  - Round table sessions: physical activity, traditional food, nutrition

  - Panel presentations: dpp, healthy heart, and community sdpi projects

  - Ann Bullock: key note speaker (historical trauma)

  - Excellent evaluations

  - Follow up travel – tribal scholarships

  - Preparation for conference: hotel logistics, outreach and registration, organizing panels and round tables, travel scholarships

- Nike Native Fitness Preparation – September 1 &2nd 2015, XXI (12)

  - Sent out to diabetes coordinators, area diabetes, health promotion disease prevention and chr coordinators, posted on web site, out of area diabetes programs, last two year participants

  - Sent W-9 to Pryor school for LY participant

  - Created flyer (Save the Date)

  - Set up registration form(s) and signed up 1rst participant

  - Set up contracts with the three hotels for trainings

  - Completed outside vendor applications with N7 program

  - Confirmation of event from Nike

- 2 interviews for health education – WEAVE project

- Completed activity logs for Spokane Wellness challenge

- Assisted SANE Project Director with registration for training

- TA to tribes and IHS with uploading text files to WebAudit, all throughout the month

- Participated/Assist  in  Cultural Exchange – Maori delegation

- Prioritizing & Managing Deadlines in a high demand job - training

- NPAIHB DMS Training preparation

- DMS/RPMS computer time

- PM, QMAN, LMR, GEN, WebAudit

- QMAN training with BRFSS specialist

  - Correspondence with participant and trainer from NF, 2013

- Tribal Leaders Diabetes Committee representative “Obesity Prevention & Treatment” presentation

- Outreach via email requesting tribal success stories based on best practices

- Technical Assistance via telephone/email

- Western tribal diabetes team responded to over 60 technical assistance calls

- Calls were received from 23 NW tribes

- 5 out of area tribes

- 4 calls with the area ADC on tribal status for audit and ta needs

- 4 communications with the national program on issues

- Multiple calls with DIRM for problem solving

- Most calls were ta on the audit: cleaning up the dms registry, entering patients on the registry, Medications, taxonomies, how o find newly diagnosed patients, web audit ta, security keys, uploading files, gestational diabetes, and getting tribal heath status reports for the tribes in grant cycle one

Meetings/Conferences

- Risky business planning

- WEAVE meeting (2)

- HPV national roundtable meeting – Atlanta

- Social Media class at NPAIHB

- Men’s/Women’s Wellness Conference-San Diego, CA

  - Wellness in the workplace workshop

- WTDP Meeting with Sharon Stanphill – final agenda and update

- OHA – final review of contract

- QBM – Great Wolf

- Web Audit Orientation Meeting

Conference Calls

- IHS let’s move in Indian country

- Reducing Risk Factors for Obesity Early in Life: the Family Spirit Home Visiting Program

- IHS let’s move in Indian country

- IHS WebAudit conference call

- Improving Health Care Delivery Data Project:  Steering Committee Quarterly Meeting

- IHS national data call

IT Department Quarterly Report for

January/February/March 2015

Overview

The Northwest Portland Area Indian Health Board has a high level of office automation and extensive information services.  The staff uses desktop computers, laptops, PDAs and office equipment that require periodic maintenance. This is in addition to 11 servers and other electronic equipment housed in a secure and temperature-controlled server room.  The Board also has a 24 station training room using Dell PCs  and Microsoft Terminal Server technology.  The purchase of technical equipment, configuration, and maintenance is handled by the department director and the network administrator.  The Meaningful Use Project is now a part of the IT Department and its activities will be part of this report.

Meetings Attended:

- NIHB – NPAIHB bi-weekly status update calls

- National MU Team meetings (every 2 weeks)

- National Pharmacy Council monthly meeting

- E-Prescribing monthly status calls

- Pharmacy PSG monthly meetings

- Area CAC conference calls weekly

- Multiple Web development meetings

Conferences and Trainings Supported/Provided:

- Winter Grant Writing Workshop

- Pharmacy Residency Informatics Course monthly session

- Regular conference calls hosted to answer MU attestation questions as deadlines for 2014 approached

- January 2015 QBM

- EHR and MU for HIM

- Nooksack e-prescribing provider training

- RPMS / Immunization Training

- RPMS - DMS Training

- Portland Area Smoking Cessation training session for I/T/U pharmacists

- SANE Training

- Tribal BEAR – HIV/HCV/STI Clinical Update Training

- WORDPRESS LEVEL II CLASS

- Social Media Basics: Getting Started and Best Practices training

- SARRC training

- HIV/HCV Clinical Update Training

Presentations:

- Pharmacy Workflow Changes with EHRp13 - national training calls

- E-prescribing and MU Stage 2 – for EHR Meet the Measures Training

- IPL training for Cow Creek staff

- IPL training for Nimiipuu staff

NPAIHB Activity:

- Site visit to Chemawa to assist with MU registration

- Assist with qualification, registration, and attestation for MU for 2014 (Nimiipuu, Fort Hall, Warm Springs, Colville, Lummi, Chemawa, Yellowhawk, Port Gamble, Coquille, Swinomish, Chehalis, Cowlitz, Tulalip, Lower Elwha, and Quinault)

- Nooksack e-prescribing deployment assistance

- Research on PQRS program and how to use RPMS to meet it

- TTAG meeting on CMS penalties and effects on Tribes

- Development of RPMS Pharmacy Best Practices

- Created multiple new accounts with corresponding card keys

- Selected web development contractors and began the website re-development process

- Completed annual Board property audit

- Setup all projects with new voice conferencing vendor MeetingOne

- Upgraded the office accounting system software

- Updated all email lists

- Configured and ordered multiple laptops and computers for Board Staff

- Initial meetings with Tracie Stevens from CSC on IHS Health IT

- ASHP Pharmacy Residency Informatics rotation precepting

- Joined PAFAC Workgroup – Regional Specialty Referral Center Benefits

- Intensive Pre and Post Install support for 2014 RPMS EHR in conjunction with Portland Area Office - including training, assistance with checklists and tasks and extensive troubleshooting after install (ongoing)

- Muckleshoot drug file review in preparation for e-prescribing

- Siletz pharmacy questions while transitioning away from RPMS

- Talking Points on Health IT for CMS Region 10 Consultation

- Lower Elwha issues with medications not crossing to PCC and lab resulting processes – in conjunction with Diabetes Audit help

- Work on national recommendations for pharmacy visit documentation in RPMS HER

- CCDA (Clinical summary in RPMS EHR) troubleshooting Yakama, Warm Springs, Colville, Cowlitz

- Nisqually – help with reminders, templates, and search reports

Outside contacts:

- Vicki French, MU Lead, USET-REC

- Carolyn Hornbuckle, NIHB REC

- Kat Goodwin, Skokomish CAC

- Nathan Town, Yakama CAC

- Ann Finkbonner, Lummi CAC

- Mary Brickell, Portland Area IT

- Cornelius Dial, Portland Area CAC

- Leatha Lynch, Siletz pharmacist

- Heather Kirkbride and Kellen Bloch, NARA

- Lori Moore, OIT E-prescribing project lead

- Carla Stearle, OIT Pharmacy consultant

- Bradley Bishop, RPMS/OIT Pharmacy liason

- Jeremiah Johnson and Jim Gemelas, Warm Springs MU team

- Amy Padilla, IHS Regional MU Consultant

- Joanne Hawkins, IHS MU Policy Analyst

- Cori Fleutsch, Chehalis

- Brandon Farley, Cow Creek

- Maranda James, Roger Saux

- Jolie Villabos, Nimiipuu

- Kelli Dennis, NHOS

- Roberta Losik, Snoqualmie

- Rhonda Nelson, Tulalip

- Kelly Samuelson and Cheryl Rasar, Swinomish

- Angie Dearing, Yellowhawk

- Pam Meyers and Destry Miller, Nooksack

- Grace Hugget, WOSU