## Slide 1
Quarterly Board Meeting
January 2015
Notes: Supported by the Native American Research Center for Health (NARCH)

## Slide 2: Native VOICES Goals
Improve our understanding of sexual norms and risk/protective factors among AI/AN youth
Produce an evidence-based HIV/STD intervention that addresses the unique needs of AI/AN youth
Offer AI/AN communities a cost-effective sexual health intervention that is readily integrated into IHS/Tribal/Urban clinical services and easily transferrable across Indian Country.
Notes: After five long years in the making…
In partnership with our NW tribes and project stakeholders - we have successfully completed all of our project goal and objectives:

## Slide 3: Adaptation Process : 2011 - 2012
FLO-0187-2DM-5N
Analyze
Interviews: Two Sprit Youth
Interviews: Clinic Staff
Focus Groups: AI Teens and Young Adults
Background, Social/Cultural Norms & Knowledge
Notes: Adaptation Process: To maximize the cultural appropriateness of the Native VOICES video, Northwest Portland Area Indian Health Board staff and project partners conducted 8 focus groups with NW Native youth, 10 interviews with clinical staff and staff at youth-serving organizations, and 13 interviews with youth who identified as LGBTQ/TS (lesbian, gay, bisexual, transgendered, or queer, or two spirit) using community-based participatory research strategies.
The findings from these focus groups were compiled in a report, and are available on the www.npaihb.org website.

## Slide 4: Adaptation Process : 2013
Notes: During the third year of the project, AI/AN teens and young adults from across the U.S. read or reenacted iterative drafts of the adapted script, and provided feedback on the characters, scenes, tone, and dialogue.
The adapted Native VOICES video was shot on location in Oklahoma City in August 2013.

## Slide 5: National Effectiveness Study – 2014
  Recruited and trained 8 sites (16 site coordinators), located across the U.S. (urban/rural)
  Randomized Sites into 3 Study Arms (800 youth, 15-24 yrs)
  Native VOICES w/ a facilitator
  Native VOICES video alone
  We R Native sexual health fact sheets
Notes: Since then, we have been working with tribes across the U.S. to evaluate the effectiveness of the Native VOICES intervention.
The sites were randomized into one of three study arms:
1. Fact sheets alone (control)
2. Fact sheets plus the Native VOICES video (intervention)
3. Fact sheets plus the Native VOICES video plus a facilitated discussion (intervention+)

## Slide 6
Notes: Together, the sites recruited and consented nearly 800 AI/AN youth 15-24 years old to participate in the Native VOICES study.

## Slide 7
March 2014 to June 2014
Recruit and Consent Youth
April-June 2014
HOST EVENTS:
Pre-Survey,
Intervention,
Post-Survey
Sep-Dec 2014
6-Month Follow-up Survey
February 2014
Sites Select Intervention Date and Location
March
2014
Receive Box of Recruitment Packets
Study Timeline
Notes: Due to the hard work and perseverance of the local site coordinators, nearly 75% of the participants completed six-month follow-up surveys.

## Slide 8
Preliminary results:
  97% - found the video to be culturally appropriate
  100% - trusted the information
  88% - felt the video showed real life situations with characters they could relate to
  89% - the video will help them make healthy life choices
  86% - could see themselves or their friends in the situations presented in the video
  94% - felt that the things the actors did and said would work for them
After watching the video, 74% felt more likely to get tested for STDs/HIV, and 61% felt more likely to use condoms.
Notes: The evaluation data will be entered, cleaned and analyzed between January-March 2015. But satisfaction surveys collected at red carpet showings of the video suggest promising results!
Over 94% of those surveyed enjoyed the video, 97% found the video to be culturally appropriate for American Indian people, and 100% felt the information could be trusted. Nearly 88% felt the video showed real life situations with characters they could relate to, and 94% thought the things the actors did and said about condoms and negotiating safe sex would work for them.
After watching the video, 74% felt more likely to get tested for STDs/HIV, and 61% felt more likely to use condoms.
The final evaluation report will be done in April 2015.

## Slide 9: Dissemination – 2015
We will mail the 43 NW tribes & the participating evaluation sites a Native VOICES Toolkit this month.
Starting on Valentine’s Day, we will release the video as a series of 6 mini-episodes on We R Native’s Facebook page and YouTube channel.
In March-April, we will have links to the video, evaluation report, and supporting documents on: www.npaihb.org/epicenter/project/native_voices_project

## Slide 10: Native VOICES Toolkit
Native VOICES video (23 minutes)
A condom demonstration video (1:40 minutes)
A dental dam demonstration video (1:08 minutes)
A selection of condoms and dental dams
A users’ guide

## Slide 11: Native VOICES Trailer: http://youtu.be/virKtMhjGCE

## Slide 12: Request a Native VOICES Toolkit
Mattie Tomeo-Palmanteer, BSW
Confederated Tribes of Colville & Yakama Nation
Project Coordinator
Northwest Portland Area Indian Health Board
2121 SW Broadway, Suite 300
Portland, Oregon 97201
Direct: (503) 416-3294
mattie@npaihb.org